ANALYSTLAB AFRICA

Project Execution Strategy

# 1. Purpose

This report explains how the ShopSmart Retail Analytics & AI Implementation Project will be delivered between 02 Nov 2026 and 01 Mar 2027 (83 working days). It covers how the project will be executed, how progress will be monitored, how risks will be managed, how communication will be kept up and how changes will be controlled. It builds on the approved Week 1 Charter, Stakeholder Register, WBS, Risk Register and Communication Plan, and on the schedule, resource plan and budget of ₦71,068,480 (including a ₦7,614,480 contingency reserve) in the Week 2 Execution Plan.

# 2. How the Project Will Be Executed

The project uses a hybrid approach. The overall plan is phase gated, with six milestones that the Sponsor approves before the next stage starts: Project Mobilized (M1), Clean Dataset and Requirements Baseline (M2), Analytics and Feature Pipeline Complete (M3), All Work stream Deliverables Built (M4), Deliverables Accepted (M5) and Project Closed (M6). Inside the four technical work streams (Data Analytics, Data Science, Machine Learning and Generative AI) the team works in two week sprints and shows working dashboards, models and copilot features to ShopSmart managers at the end of each sprint. This gives the discipline that senior management needs and the quick feedback that analytics and AI work depends on.

- Governance. The ShopSmart CEO is the Sponsor and approves gates. A Steering Committee (CEO, COO, Finance Manager, IT Manager and Project Manager) meets monthly. The Project Manager runs delivery day to day.

- Work packages. Each of the 32 activities has a named role, dates, predecessors and a clear deliverable, so completion is judged on evidence.

- Work stream coordination. Data Science cleans and validates the data first (M2), then Analytics, Machine Learning and Generative AI run in parallel from the same clean dataset. The Project Manager protects the critical path first, which runs through data cleaning, feature engineering, the modeling chain and the testing phase.

- Quality gates. A phase closes only when its exit criteria are met: reconciled data (M2), working work stream deliverables (M4) and a signed UAT and closed defects (M5).

# 3. How Progress Will Be Monitored

Progress is measured against the approved baseline. The Project Manager updates the schedule every Friday, issues a one page status report with a red, amber or green rating, and reviews the float of every open activity.

| Indicator | How it is measured | Amber trigger | Red trigger |
| --- | --- | --- | --- |
| Schedule Performance Index (SPI) | Earned value divided by planned value | Below 0.90 | Below 0.80 |
| Cost Performance Index (CPI) | Earned value divided by actual cost | Below 0.95 | Below 0.85 |
| Critical path float | Days of float on critical and near critical activities | Float below 3 days | Any slip on a zero float activity |
| Milestone variance | Forecast date minus baseline date for the next gate | More than 2 days | More than 5 days |
| Quality | Data reconciliation, open defects, model accuracy, copilot answer accuracy | Target missed by up to 10% | Target missed by more than 10% |

Spend is compared with the budget every month, and API and cloud usage is checked weekly through usage alerts. A red indicator is escalated to the Sponsor within one working day with a recovery proposal.

# 4. How Project Risks Will Be Managed

Risks follow a four step cycle: identify, assess, respond and monitor. Each risk in the register has a probability and impact score, a mitigation strategy, a contingency plan and an owner. The register is reviewed weekly with the team and the top risks are reported to the Steering Committee each month. The highest scoring risks are:

| Risk | Score | Main response | Owner |
| --- | --- | --- | --- |
| R01 Poor data quality | 20 High | Profile early (A04), documented cleaning rules (A05), reconcile to source (A06), quality gate at M2 | Data Scientist |
| R03 Delayed deliverables | 12 Medium | Weekly float review, early warning at a 2 day slip, add resource or run tasks in parallel | Project Manager |
| R04 Scope creep | 12 Medium | Scope baseline at M2, change control, backlog for new requests | Project Manager |
| R05 API limitations | 12 Medium | Test quotas early (A19), usage caps, caching, provider can be swapped | Generative AI Engineer |
| R08 Technical integration issues | 12 Medium | Fixed environment list, shared GitHub rules, early test in A22, file based fallback | Machine Learning Engineer |

The contingency reserve of ₦7,614,480 (12% of the base budget) is split across four risk themes: data quality and missing records, delivery delays, API limits and integration, and budget and scope changes. The Project Manager may release up to ₦500,000 per event. Larger releases need Sponsor approval, and every release is logged against the risk that caused it.

# 5. How Communication Will Be Maintained

Communication follows the approved Communication Plan, owned by the Project Manager, and becomes more frequent if the project status turns amber or red.

- Daily: 15 minute team stand up and a shared task board for blockers.

- Weekly: status report to the CEO and COO, and a critical path and risk review with the team.

- Fortnightly: sprint demonstration to the Sales, Inventory, Store and IT managers.

- Monthly: Steering Committee on progress, budget, risks and decisions.

- At each milestone: a formal gate review and sign off, recorded in the decision log.

Issues follow the escalation matrix, from work stream owner to Project Manager to Sponsor to Steering Committee, with a time limit at each level. All documents sit in one controlled repository with version numbers.

# 6. How Project Changes Will Be Controlled

Any change to scope, schedule or budget after the M2 baseline follows one process: (1) the requester submits a change request; (2) the Project Manager logs it and assesses the impact on scope, time, cost, risk and quality within three working days; (3) it is approved, rejected or deferred at the right level; (4) approved changes are added to the plan and the baseline is reissued with a new version number; (5) affected people are told. Authority is tiered:

| Level | Impact | Decision maker |
| --- | --- | --- |
| Tier 1 | No effect on the critical path, within existing float, and up to ₦500,000 | Project Manager |
| Tier 2 | Critical path slip of up to 5 days, or cost between ₦500,000 and ₦3,500,000, or a minor scope change | Sponsor (CEO) |
| Tier 3 | Critical path slip above 5 days, cost above ₦3,500,000, or any change to objectives or the out of scope list | Steering Committee |

Valuable but non urgent requests go into a backlog for a later phase. This protects the approved scope and the finish date of 01 Mar 2027.

# 7. Conclusion

This strategy gives the project clear gates, measurable indicators, an owner for every risk and a controlled route for change. With the Gantt chart, critical path analysis, resource plan and budget, it gives ShopSmart and AnalystLab a plan that can be approved and then delivered from 02 Nov 2026.