## Assumptions
ShopSmart Retail Analytics & AI Implementation Project
AnalystLab Africa PM Internship, Week 2: Assumptions and legend
Project start date | 2026-11-02
Working week | Monday to Friday
Currency | Nigerian Naira (indicative estimates)
Non working days (Nigerian public holidays)
Christmas Day | 2026-12-25
Boxing Day (observed) | 2026-12-28
New Year's Day | 2027-01-01
Good Friday | 2027-03-26
Easter Monday | 2027-03-29
Workers' Day (observed) | 2027-05-03
Legend
Blue text | Input (change to re-plan: start date, holidays, durations, quantities, rates)
Black text | Formula (do not overwrite)
Yellow cell | Key assumption: project start date
Key planning assumptions
1. All dependencies are Finish to Start with no lag.
2. Durations are in working days. Dates calculate from the start date, skipping weekends and listed holidays.
3. Moveable religious holidays (for example Eid) are not pre loaded. Add them to the holiday list if declared.
4. Critical path uses the Critical Path Method (forward and backward pass). Float = Late Start minus Early Start.
5. Costs are indicative Naira estimates built from role day rates, licence prices and cloud run rates.
6. Contingency reserve is 12% of the base budget because data quality, API limits and price changes add uncertainty.
7. The Week 1 baseline (Charter, Scope Statement, WBS, Risk Register, Communication Plan) is approved. Out of scope: ERP, mobile apps, live production deployment, payment gateway, loyalty system.

## Schedule
Activity ID | Activity Name | Phase | Duration (days) | Start Date | Finish Date | Dependencies (Predecessors) | Assigned Resource | Early Start (day) | Early Finish (day) | Late Start (day) | Late Finish (day) | Total Float (days) | Critical?
A01 | Project kick-off and sign-off of execution plan | 1. Initiation & Mobilisation | 2 | 2026-11-02 | 2026-11-03 | None | Project Manager | 0 | 2 | 0 | 2 | 0 | Yes
A02 | Tools, access and environment setup (Power BI, Python, GitHub, API keys) | 1. Initiation & Mobilisation | 3 | 2026-11-04 | 2026-11-06 | A01 | Project Manager, Data Analyst | 2 | 5 | 3 | 6 | 1 | No
A03 | Dataset handover and file validation (9 CSV files and data dictionary) | 1. Initiation & Mobilisation | 4 | 2026-11-04 | 2026-11-09 | A01 | Business Analyst, Data Analyst | 2 | 6 | 2 | 6 | 0 | Yes
M1 | Milestone: Project Mobilised | 1. Initiation & Mobilisation | 0 | 2026-11-09 | 2026-11-09 | A02, A03 | Project Manager | 6 | 6 | 6 | 6 | 0 | Yes
A04 | Data profiling and quality assessment | 2. Data Preparation & Requirements | 5 | 2026-11-10 | 2026-11-16 | M1 | Data Scientist, Data Analyst | 6 | 11 | 6 | 11 | 0 | Yes
A05 | Data cleaning and standardisation | 2. Data Preparation & Requirements | 8 | 2026-11-17 | 2026-11-26 | A04 | Data Scientist, Data Analyst | 11 | 19 | 11 | 19 | 0 | Yes
A06 | Data validation and reconciliation checks | 2. Data Preparation & Requirements | 4 | 2026-11-27 | 2026-12-02 | A05 | Data Scientist, QA Tester | 19 | 23 | 19 | 23 | 0 | Yes
A07 | Requirements workshops with ShopSmart managers | 2. Data Preparation & Requirements | 6 | 2026-11-10 | 2026-11-17 | M1 | Business Analyst, Project Manager | 6 | 12 | 17 | 23 | 11 | No
M2 | Milestone: Clean Dataset and Requirements Baselined | 2. Data Preparation & Requirements | 0 | 2026-12-02 | 2026-12-02 | A06, A07 | Project Manager | 23 | 23 | 23 | 23 | 0 | Yes
A08 | Exploratory data analysis and statistical insights | 3. Data Analytics & Data Science | 7 | 2026-12-03 | 2026-12-11 | M2 | Data Scientist | 23 | 30 | 23 | 30 | 0 | Yes
A09 | Sales dashboard development | 3. Data Analytics & Data Science | 8 | 2026-12-03 | 2026-12-14 | M2 | Data Analyst | 23 | 31 | 41 | 49 | 18 | No
A10 | Customer dashboard development | 3. Data Analytics & Data Science | 7 | 2026-12-03 | 2026-12-11 | M2 | Data Analyst | 23 | 30 | 42 | 49 | 19 | No
A11 | Store performance dashboard development | 3. Data Analytics & Data Science | 6 | 2026-12-15 | 2026-12-22 | A09 | Data Analyst | 31 | 37 | 49 | 55 | 18 | No
A12 | Inventory dashboard development | 3. Data Analytics & Data Science | 6 | 2026-12-14 | 2026-12-21 | A10 | Data Analyst | 30 | 36 | 49 | 55 | 19 | No
A13 | Executive analytics report | 3. Data Analytics & Data Science | 4 | 2026-12-23 | 2026-12-30 | A11, A12 | Business Analyst, Data Analyst | 37 | 41 | 55 | 59 | 18 | No
A14 | Feature engineering pipeline | 3. Data Analytics & Data Science | 8 | 2026-12-14 | 2026-12-23 | A08 | Data Scientist | 30 | 38 | 30 | 38 | 0 | Yes
M3 | Milestone: Analytics and Feature Pipeline Complete | 3. Data Analytics & Data Science | 0 | 2026-12-30 | 2026-12-30 | A13, A14 | Project Manager | 41 | 41 | 59 | 59 | 18 | No
A15 | Sales forecasting model development | 4. Machine Learning | 12 | 2026-12-24 | 2027-01-13 | A14 | Machine Learning Engineer | 38 | 50 | 42 | 54 | 4 | No
A16 | Customer segmentation model | 4. Machine Learning | 8 | 2026-12-24 | 2027-01-07 | A14 | Data Scientist | 38 | 46 | 38 | 46 | 0 | Yes
A17 | Product recommendation prototype | 4. Machine Learning | 8 | 2027-01-08 | 2027-01-19 | A16 | Data Scientist, Machine Learning Engineer | 46 | 54 | 46 | 54 | 0 | Yes
A18 | Model evaluation and evaluation report | 4. Machine Learning | 5 | 2027-01-20 | 2027-01-26 | A15, A17 | Machine Learning Engineer, QA Tester | 54 | 59 | 54 | 59 | 0 | Yes
A19 | Prompt library design and testing | 5. Generative AI | 8 | 2026-12-03 | 2026-12-14 | M2 | Generative AI Engineer | 23 | 31 | 27 | 35 | 4 | No
A20 | Retail report generator | 5. Generative AI | 7 | 2026-12-15 | 2026-12-23 | A19 | Generative AI Engineer | 31 | 38 | 35 | 42 | 4 | No
A21 | AI Retail Copilot development (Streamlit) | 5. Generative AI | 12 | 2026-12-24 | 2027-01-13 | A20 | Generative AI Engineer | 38 | 50 | 42 | 54 | 4 | No
A22 | Copilot integration with data and forecasting model | 5. Generative AI | 5 | 2027-01-14 | 2027-01-20 | A21, A15 | Generative AI Engineer, Machine Learning Engineer | 50 | 55 | 54 | 59 | 4 | No
M4 | Milestone: All Workstream Deliverables Built | 6. Testing & Quality Assurance | 0 | 2027-01-26 | 2027-01-26 | A18, A22, M3 | Project Manager | 59 | 59 | 59 | 59 | 0 | Yes
A23 | Dashboard quality review and data accuracy testing | 6. Testing & Quality Assurance | 4 | 2027-01-27 | 2027-02-01 | M4 | QA Tester, Data Analyst | 59 | 63 | 61 | 65 | 2 | No
A24 | Code review and model testing | 6. Testing & Quality Assurance | 5 | 2027-01-27 | 2027-02-02 | M4 | QA Tester, Machine Learning Engineer | 59 | 64 | 60 | 65 | 1 | No
A25 | Copilot testing and prompt evaluation | 6. Testing & Quality Assurance | 6 | 2027-01-27 | 2027-02-03 | M4 | QA Tester, Generative AI Engineer | 59 | 65 | 59 | 65 | 0 | Yes
A26 | User acceptance testing with ShopSmart managers | 6. Testing & Quality Assurance | 5 | 2027-02-04 | 2027-02-10 | A23, A24, A25 | Business Analyst, QA Tester | 65 | 70 | 65 | 70 | 0 | Yes
A27 | Defect fixing and retesting | 6. Testing & Quality Assurance | 5 | 2027-02-11 | 2027-02-17 | A26 | Data Analyst, Machine Learning Engineer, Generative AI Engineer | 70 | 75 | 70 | 75 | 0 | Yes
M5 | Milestone: Deliverables Accepted | 6. Testing & Quality Assurance | 0 | 2027-02-17 | 2027-02-17 | A27 | Project Manager | 75 | 75 | 75 | 75 | 0 | Yes
A28 | Project and technical documentation | 7. Documentation, Presentation & Closure | 7 | 2027-01-27 | 2027-02-04 | M4 | Project Manager, Business Analyst | 59 | 66 | 68 | 75 | 9 | No
A29 | User training and handover sessions | 7. Documentation, Presentation & Closure | 3 | 2027-02-18 | 2027-02-22 | M5 | Business Analyst, Data Analyst | 75 | 78 | 76 | 79 | 1 | No
A30 | Final business presentation preparation | 7. Documentation, Presentation & Closure | 4 | 2027-02-18 | 2027-02-23 | M5, A28 | Project Manager, Data Analyst | 75 | 79 | 75 | 79 | 0 | Yes
A31 | Final presentation to ShopSmart leadership | 7. Documentation, Presentation & Closure | 1 | 2027-02-24 | 2027-02-24 | A29, A30 | Project Manager | 79 | 80 | 79 | 80 | 0 | Yes
A32 | Project closure, lessons learned and repository finalisation | 7. Documentation, Presentation & Closure | 3 | 2027-02-25 | 2027-03-01 | A31 | Project Manager | 80 | 83 | 80 | 83 | 0 | Yes
M6 | Milestone: Project Closed | 7. Documentation, Presentation & Closure | 0 | 2027-03-01 | 2027-03-01 | A32 | Project Manager | 83 | 83 | 83 | 83 | 0 | Yes
| Total project duration (working days) |  | 83
| Planned project finish date |  | 2027-03-01
| Number of activities (excluding milestones) |  | 32
| Number of milestones |  | 6
Formulas:
Start Date = WORKDAY(Assumptions!$C4-1,[Early Start (day)]+1,Assumptions!$C9:C14)
Start Date = [Finish Date]
Finish Date = WORKDAY(Assumptions!$C4-1,[Early Finish (day)],Assumptions!$C9:C14)

## Gantt Chart
Gantt Chart (weekly view)
ID | Activity / Phase | Start | Finish | Critical? | Type | Predecessors | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01
P1 | INITIATION & MOBILISATION | 2026-11-02 | 2026-11-09 |  | Phase
A01 | Project kick-off and sign-off of execution plan | 2026-11-02 | 2026-11-03 | Yes | Activity | None
A02 | Tools, access and environment setup (Power BI, Python, GitHub, API keys) | 2026-11-04 | 2026-11-06 | No | Activity | A01
A03 | Dataset handover and file validation (9 CSV files and data dictionary) | 2026-11-04 | 2026-11-09 | Yes | Activity | A01
M1 | Milestone: Project Mobilised | 2026-11-09 | 2026-11-09 | Yes | Milestone | A02, A03 | bar: 2026-11-09
P2 | DATA PREPARATION & REQUIREMENTS | 2026-11-10 | 2026-12-02 |  | Phase
A04 | Data profiling and quality assessment | 2026-11-10 | 2026-11-16 | Yes | Activity | M1
A05 | Data cleaning and standardisation | 2026-11-17 | 2026-11-26 | Yes | Activity | A04
A06 | Data validation and reconciliation checks | 2026-11-27 | 2026-12-02 | Yes | Activity | A05
A07 | Requirements workshops with ShopSmart managers | 2026-11-10 | 2026-11-17 | No | Activity | M1
M2 | Milestone: Clean Dataset and Requirements Baselined | 2026-12-02 | 2026-12-02 | Yes | Milestone | A06, A07 | bar: 2026-11-30
P3 | DATA ANALYTICS & DATA SCIENCE | 2026-12-03 | 2026-12-30 |  | Phase
A08 | Exploratory data analysis and statistical insights | 2026-12-03 | 2026-12-11 | Yes | Activity | M2
A09 | Sales dashboard development | 2026-12-03 | 2026-12-14 | No | Activity | M2
A10 | Customer dashboard development | 2026-12-03 | 2026-12-11 | No | Activity | M2
A11 | Store performance dashboard development | 2026-12-15 | 2026-12-22 | No | Activity | A09
A12 | Inventory dashboard development | 2026-12-14 | 2026-12-21 | No | Activity | A10
A13 | Executive analytics report | 2026-12-23 | 2026-12-30 | No | Activity | A11, A12
A14 | Feature engineering pipeline | 2026-12-14 | 2026-12-23 | Yes | Activity | A08
M3 | Milestone: Analytics and Feature Pipeline Complete | 2026-12-30 | 2026-12-30 | No | Milestone | A13, A14 | bar: 2026-12-28
P4 | MACHINE LEARNING | 2026-12-24 | 2027-01-26 |  | Phase
A15 | Sales forecasting model development | 2026-12-24 | 2027-01-13 | No | Activity | A14
A16 | Customer segmentation model | 2026-12-24 | 2027-01-07 | Yes | Activity | A14
A17 | Product recommendation prototype | 2027-01-08 | 2027-01-19 | Yes | Activity | A16
A18 | Model evaluation and evaluation report | 2027-01-20 | 2027-01-26 | Yes | Activity | A15, A17
P5 | GENERATIVE AI | 2026-12-03 | 2027-01-20 |  | Phase
A19 | Prompt library design and testing | 2026-12-03 | 2026-12-14 | No | Activity | M2
A20 | Retail report generator | 2026-12-15 | 2026-12-23 | No | Activity | A19
A21 | AI Retail Copilot development (Streamlit) | 2026-12-24 | 2027-01-13 | No | Activity | A20
A22 | Copilot integration with data and forecasting model | 2027-01-14 | 2027-01-20 | No | Activity | A21, A15
P6 | TESTING & QUALITY ASSURANCE | 2027-01-26 | 2027-02-17 |  | Phase
M4 | Milestone: All Workstream Deliverables Built | 2027-01-26 | 2027-01-26 | Yes | Milestone | A18, A22, M3 | bar: 2027-01-25
A23 | Dashboard quality review and data accuracy testing | 2027-01-27 | 2027-02-01 | No | Activity | M4
A24 | Code review and model testing | 2027-01-27 | 2027-02-02 | No | Activity | M4
A25 | Copilot testing and prompt evaluation | 2027-01-27 | 2027-02-03 | Yes | Activity | M4
A26 | User acceptance testing with ShopSmart managers | 2027-02-04 | 2027-02-10 | Yes | Activity | A23, A24, A25
A27 | Defect fixing and retesting | 2027-02-11 | 2027-02-17 | Yes | Activity | A26
M5 | Milestone: Deliverables Accepted | 2027-02-17 | 2027-02-17 | Yes | Milestone | A27 | bar: 2027-02-15
P7 | DOCUMENTATION, PRESENTATION & CLOSURE | 2027-01-27 | 2027-03-01 |  | Phase
A28 | Project and technical documentation | 2027-01-27 | 2027-02-04 | No | Activity | M4
A29 | User training and handover sessions | 2027-02-18 | 2027-02-22 | No | Activity | M5
A30 | Final business presentation preparation | 2027-02-18 | 2027-02-23 | Yes | Activity | M5, A28
A31 | Final presentation to ShopSmart leadership | 2027-02-24 | 2027-02-24 | Yes | Activity | A29, A30
A32 | Project closure, lessons learned and repository finalisation | 2027-02-25 | 2027-03-01 | Yes | Activity | A31
M6 | Milestone: Project Closed | 2027-03-01 | 2027-03-01 | Yes | Milestone | A32 | bar: 2027-03-01

## Critical Path
Critical Path Analysis
Total project duration (working days) |  | 83
Project start date |  | 2026-11-02
Project finish date |  | 2027-03-01
Critical activities (excluding milestones) |  | 16
Activities with float |  | 16
Table 1: Critical path (zero float), in sequence
ID | Activity | Duration | Start | Finish | Float
A01 | Project kick-off and sign-off of execution plan | 2 | 2026-11-02 | 2026-11-03 | 0
A03 | Dataset handover and file validation (9 CSV files and data dictionary) | 4 | 2026-11-04 | 2026-11-09 | 0
M1 | Milestone: Project Mobilised | 0 | 2026-11-09 | 2026-11-09 | 0
A04 | Data profiling and quality assessment | 5 | 2026-11-10 | 2026-11-16 | 0
A05 | Data cleaning and standardisation | 8 | 2026-11-17 | 2026-11-26 | 0
A06 | Data validation and reconciliation checks | 4 | 2026-11-27 | 2026-12-02 | 0
M2 | Milestone: Clean Dataset and Requirements Baselined | 0 | 2026-12-02 | 2026-12-02 | 0
A08 | Exploratory data analysis and statistical insights | 7 | 2026-12-03 | 2026-12-11 | 0
A14 | Feature engineering pipeline | 8 | 2026-12-14 | 2026-12-23 | 0
A16 | Customer segmentation model | 8 | 2026-12-24 | 2027-01-07 | 0
A17 | Product recommendation prototype | 8 | 2027-01-08 | 2027-01-19 | 0
A18 | Model evaluation and evaluation report | 5 | 2027-01-20 | 2027-01-26 | 0
M4 | Milestone: All Workstream Deliverables Built | 0 | 2027-01-26 | 2027-01-26 | 0
A25 | Copilot testing and prompt evaluation | 6 | 2027-01-27 | 2027-02-03 | 0
A26 | User acceptance testing with ShopSmart managers | 5 | 2027-02-04 | 2027-02-10 | 0
A27 | Defect fixing and retesting | 5 | 2027-02-11 | 2027-02-17 | 0
M5 | Milestone: Deliverables Accepted | 0 | 2027-02-17 | 2027-02-17 | 0
A30 | Final business presentation preparation | 4 | 2027-02-18 | 2027-02-23 | 0
A31 | Final presentation to ShopSmart leadership | 1 | 2027-02-24 | 2027-02-24 | 0
A32 | Project closure, lessons learned and repository finalisation | 3 | 2027-02-25 | 2027-03-01 | 0
M6 | Milestone: Project Closed | 0 | 2027-03-01 | 2027-03-01 | 0
Table 2: Activities with float
ID | Activity | Duration | Start | Finish | Float (days)
A02 | Tools, access and environment setup (Power BI, Python, GitHub, API keys) | 3 | 2026-11-04 | 2026-11-06 | 1
A07 | Requirements workshops with ShopSmart managers | 6 | 2026-11-10 | 2026-11-17 | 11
A09 | Sales dashboard development | 8 | 2026-12-03 | 2026-12-14 | 18
A10 | Customer dashboard development | 7 | 2026-12-03 | 2026-12-11 | 19
A11 | Store performance dashboard development | 6 | 2026-12-15 | 2026-12-22 | 18
A12 | Inventory dashboard development | 6 | 2026-12-14 | 2026-12-21 | 19
A13 | Executive analytics report | 4 | 2026-12-23 | 2026-12-30 | 18
A15 | Sales forecasting model development | 12 | 2026-12-24 | 2027-01-13 | 4
A19 | Prompt library design and testing | 8 | 2026-12-03 | 2026-12-14 | 4
A20 | Retail report generator | 7 | 2026-12-15 | 2026-12-23 | 4
A21 | AI Retail Copilot development (Streamlit) | 12 | 2026-12-24 | 2027-01-13 | 4
A22 | Copilot integration with data and forecasting model | 5 | 2027-01-14 | 2027-01-20 | 4
A23 | Dashboard quality review and data accuracy testing | 4 | 2027-01-27 | 2027-02-01 | 2
A24 | Code review and model testing | 5 | 2027-01-27 | 2027-02-02 | 1
A28 | Project and technical documentation | 7 | 2027-01-27 | 2027-02-04 | 9
A29 | User training and handover sessions | 3 | 2027-02-18 | 2027-02-22 | 1
Formulas:
Start = INDEX(Schedule!$F5:F47,MATCH([ID],Schedule!$B5:B47,0))
Finish = INDEX(Schedule!$G5:G47,MATCH([ID],Schedule!$B5:B47,0))

## Resources
Resource Allocation Plan
Utilisation = budgeted days per person divided by total project duration.
1. Human Resources
Role | Qty | Days per person | Utilisation of project duration | Key responsibilities | Main activities
Project Manager | 1 | 83 | 100% | Plan, schedule, budget, risks, reporting, stakeholder management, change control | A01, A02, A07, A28, A30 to A32
Business Analyst | 1 | 40 | 48.19% | Requirements, stakeholder workshops, UAT coordination, user training | A03, A07, A13, A26, A28, A29
Data Analyst | 2 | 45 | 54.22% | Dashboards, data cleaning support, executive reporting | A02 to A06, A09 to A13, A23, A27, A29, A30
Data Scientist | 1 | 50 | 60.24% | Data profiling and cleaning, exploratory analysis, feature engineering, segmentation | A04 to A06, A08, A14, A16, A17
Machine Learning Engineer | 1 | 40 | 48.19% | Forecasting model, recommendation prototype, model evaluation, integration | A15, A17, A18, A22, A24, A27
Generative AI Engineer | 1 | 45 | 54.22% | Prompt library, report generator, Streamlit Retail Copilot | A19 to A22, A25, A27
QA Tester | 1 | 25 | 30.12% | Data validation, code review, testing, UAT support | A06, A18, A23 to A26
2. Software Resources
Tool | Purpose | Users | Used in activities
Power BI Pro | Dashboards and sharing with managers | 12 users | A09 to A13, A23, A26
Python and Jupyter Notebook (open source) | Cleaning, analysis, feature engineering, modelling | Data team | A04 to A22
VS Code (free) | Code development and review | Data team | A14 to A27
GitHub | Version control and project repository | 8 users | A02 to A32
Streamlit (open source) | Interface for the AI Retail Copilot | GenAI engineer | A21, A22
OpenAI or Gemini API | Language model for the copilot and report generator | GenAI engineer | A19 to A25
Jira or ClickUp | Task tracking and status reporting | 8 users | All
3. Hardware Resources
Item | Qty | Purpose | Needed for
High spec laptops | 2 | Model training and copilot development | A15 to A22
External drives and peripherals | 8 | Data transfer and workstation set up | A02, A03
Secure backup storage device | 1 | Backup of cleaned datasets and models | A05 to A32
4. External Services
Service | Purpose | Linked activity
Data protection adviser | Review of NDPA compliance for customer data | A04, A19
Independent security reviewer | Security review of the AI Retail Copilot | A25
Venue and logistics provider | Workshops and final presentation | A07, A31
5. Team Responsibilities (RACI: R Responsible, A Accountable, C Consulted, I Informed)
Deliverable | Sponsor | PM | BA | DA | DS | MLE | GAI | QA | ShopSmart
Execution plan and governance | A | R | C | I | I | I | I | I | C
Data profiling, cleaning and validation | I | A | C | R | R | I | I | C | I
Requirements and workshops | C | A | R | C | C | C | C | I | C
Dashboards and executive report | I | A | C | R | C | I | I | C | C
Feature engineering and statistical insights | I | A | C | C | R | C | I | I | I
Forecasting and segmentation models | I | A | C | I | R | R | I | C | I
Prompt library and AI Retail Copilot | I | A | C | I | I | C | R | C | C
Testing and defect resolution | I | A | C | C | C | C | C | R | I
UAT and acceptance | A | R | R | C | I | I | I | C | C
Training, final presentation and closure | A | R | C | C | I | I | I | I | C

## Budget
Project Budget (NGN)
Total = Qty x Unit cost x Duration/Multiplier. Contingency is a percentage of the base budget.
Budget summary
Category | Amount (NGN) | % of total budget | Contingency rate
Personnel | 49100000 | 69.09% | of base budget | 12%
Software Licences | 1504000 | 2.116%
Hardware | 4330000 | 6.093%
Cloud Services | 3120000 | 4.39%
External Services | 3300000 | 4.643%
Training | 2100000 | 2.955%
Base budget (subtotal) | 63454000 | 89.29%
Contingency reserve | 7614480 | 10.71%
TOTAL PROJECT BUDGET | 71068480 | 100%
Contingency allocation
Risk theme | Share | Amount (NGN)
Data quality and missing records | 35% | 2665068
Delivery delays and schedule pressure | 25% | 1903620
API limits and technical integration | 25% | 1903620
Budget, price changes and scope changes | 15% | 1142172
Total contingency | 100% | 7614480
Detailed cost estimate
Category | Item | Basis | Qty | Unit cost (NGN) | Duration / Multiplier | Total (NGN)
Personnel | Project Manager | 1 FTE for the full duration (days per person x day rate) | 1 | 150000 | 83 | 12450000
Personnel | Business Analyst | Requirements, UAT, training (days per person x day rate) | 1 | 120000 | 40 | 4800000
Personnel | Data Analyst | 2 people, dashboards and data support (days per person x day rate) | 2 | 100000 | 45 | 9000000
Personnel | Data Scientist | Cleaning, EDA, features, segmentation (days per person x day rate) | 1 | 140000 | 50 | 7000000
Personnel | Machine Learning Engineer | Forecasting and recommendation models (days per person x day rate) | 1 | 160000 | 40 | 6400000
Personnel | Generative AI Engineer | Prompt library and AI Retail Copilot (days per person x day rate) | 1 | 160000 | 45 | 7200000
Personnel | QA Tester | Validation, code review, testing (days per person x day rate) | 1 | 90000 | 25 | 2250000
Software Licences | Power BI Pro licences | 12 users, 4 months | 12 | 22000 | 4 | 1056000
Software Licences | GitHub Team | 8 users, 4 months | 8 | 6000 | 4 | 192000
Software Licences | Project tracking tool (Jira or ClickUp) | 8 users, 4 months | 8 | 8000 | 4 | 256000
Software Licences | Open source tools (Python, Jupyter, VS Code, Streamlit) | No licence fee | 1 | 0 | 1 | 0
Hardware | High spec laptops for model training | Purchase | 2 | 1800000 | 1 | 3600000
Hardware | External drives and peripherals | Purchase | 8 | 60000 | 1 | 480000
Hardware | Secure backup storage device | Purchase | 1 | 250000 | 1 | 250000
Cloud Services | LLM API usage (OpenAI or Gemini) for development and testing | Monthly, 4 months | 1 | 450000 | 4 | 1800000
Cloud Services | Cloud storage and compute for model training | Monthly, 4 months | 1 | 250000 | 4 | 1000000
Cloud Services | Streamlit prototype hosting | Monthly, 4 months | 1 | 80000 | 4 | 320000
External Services | Data protection (NDPA) review | Fixed fee | 1 | 1500000 | 1 | 1500000
External Services | Independent security review of the AI Retail Copilot | Fixed fee | 1 | 1200000 | 1 | 1200000
External Services | Workshop and final presentation logistics | Fixed fee | 1 | 600000 | 1 | 600000
Training | Team upskilling (Power BI and prompt engineering) | 8 team members | 8 | 75000 | 1 | 600000
Training | ShopSmart manager training sessions | 3 sessions | 3 | 400000 | 1 | 1200000
Training | Training materials and user guides | Fixed | 1 | 300000 | 1 | 300000