ANALYSTLAB AFRICA

Project Management Internship Program |  Week 2 | Parts 2 to 6

Project Execution Plan

| Program | Project Management Internship |
| --- | --- |
| Week | Week 2 |
| Project | Project Scheduling & Execution Planning: ShopSmart Retail Analytics & AI Implementation Project |
| Version | 1.0 |
| Issue Date | 26 October 2026 |
| Prepared by | Opeyemi Princess Dothan, Junior Project Manager |
| Submission Deadline | As per program brief (Wednesday, 11:59 ) |
| Related files | Project_Schedule_Planning_Workbook.xlsx, Gantt_Chart.png, Updated_Week1_Project_Documents.docx, Project_Execution_Strategy.docx |

# 1. Executive Summary

The Week 1 planning documents (Charter, Stakeholder Register, WBS, Risk Register and Communication Plan) were approved and the ShopSmart project now moves into Execution Planning. This plan gives senior management a detailed schedule, Gantt chart, critical path analysis, resource allocation plan and budget. The project will run from 02 Nov 2026 to 01 Mar 2027, duration of 83 working days (about 17 weeks), using 32 activities and 6 milestones. The estimated budget is ₦71,068,480, including a ₦7,614,480 contingency reserve.

| Measure | Value |
| --- | --- |
| Start date | 02 Nov 2026 |
| Finish date | 01 Mar 2027 |
| Duration | 83 working days |
| Activities and milestones | 32 activities, 6 milestones, 7 phases |
| Critical path | 16 critical activities; 16 activities with float |
| Team | 8 people across 7 roles |
| Total budget | ₦71,068,480 (base ₦63,454,000 plus contingency ₦7,614,480) |

## Phase summary

| Phase | Name | Start | Finish | Working days |
| --- | --- | --- | --- | --- |
| 1 | Initiation & Mobilization | 02 Nov 2026 | 09 Nov 2026 | 6 |
| 2 | Data Preparation & Requirements | 10 Nov 2026 | 02 Dec 2026 | 17 |
| 3 | Data Analytics & Data Science | 03 Dec 2026 | 30 Dec 2026 | 18 |
| 4 | Machine Learning | 24 Dec 2026 | 26 Jan 2027 | 21 |
| 5 | Generative AI | 03 Dec 2026 | 20 Jan 2027 | 32 |
| 6 | Testing & Quality Assurance | 27 Jan 2027 | 17 Feb 2027 | 16 |
| 7 | Documentation, Presentation & Closure | 27 Jan 2027 | 01 Mar 2027 | 24 |

# 2. Answers to the Business Questions

| # | Question | Answer |
| --- | --- | --- |
| 1 | What is the overall project timeline? | 02 Nov 2026 to 01 Mar 2027: 83 working days across seven phases. Weekends and three Nigerian public holidays (25 December, 28 December and 1 January) are excluded. See the phase summary above and the Gantt chart. |
| 2 | Which tasks are dependent on one another? | All dependencies are Finish to Start. The main chain is Discovery, Design, Build, Testing, Deployment, and Closure. Examples: A05 cleaning needs A04 profiling; A14 feature engineering needs A08 EDA; the forecasting and segmentation models (A15, A16) need A14; A22 copilot integration needs A21 and A15; M4 needs A18, A22 and M3; A26 UAT needs A23, A24 and A25. The full predecessor list is in Section 3. |
| 3 | Which activities are on the Critical Path? | 16 activities with zero float: A01, A03, A04, A05, A06, A08, A14, A16, A17, A18, A25, A26, A27, A30, A31, A32. Total duration 83 working days. See Section 5. |
| 4 | How should project resources be allocated? | 8 people across 7 roles, loaded and protected on critical activities first. Software, hardware, cloud and external services are listed against the activities that need them. See Section 6. |
| 5 | What is the estimated project budget? | ₦71,068,480: personnel ₦49,100,000, software ₦1,504,000, hardware ₦4,330,000, cloud ₦3,120,000, external services ₦3,300,000, training ₦2,100,000, contingency ₦7,614,480. See Section 7. |
| 6 | Which milestones indicate successful project progress? | M1 Project Mobilized (09 Nov 2026); M2 Clean Dataset and Requirements Baseline (02 Dec 2026); M3 Analytics and Feature Pipeline Complete (30 Dec 2026); M4 All Work stream Deliverables Built (26 Jan 2027); M5 Deliverables Accepted (17 Feb 2027); M6 Project Closed (01 Mar 2027). Each is a formal gate approved by the Executive Sponsor. |
| 7 | How will project execution be monitored? | Weekly schedule update and RAG status report; SPI and CPI tracking; weekly critical path and float review; monthly Steering Committee; milestone gate reviews; weekly risk review. Details are in the Project Execution Strategy. |

# 3. Project Schedule

Durations are in working days. Dates are calculated from the start date and exclude weekends and public holidays. Float is total float in working days. Full formulas are in the Excel workbook.

| ID | Activity | Dur. | Start | Finish | Dependencies | Assigned Resource | Float |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P1 | PHASE 1: INITIATION & MOBILISATION |  |  |  |  |  |  |
| A01 | Project kick-off and sign-off of execution plan | 2 | 02 Nov 2026 | 03 Nov 2026 | None | Project Manager | 0 Critical |
| A02 | Tools, access and environment setup (Power BI, Python, GitHub, API keys) | 3 | 04 Nov 2026 | 06 Nov 2026 | A01 | Project Manager, Data Analyst | 1 |
| A03 | Dataset handover and file validation (9 CSV files and data dictionary) | 4 | 04 Nov 2026 | 09 Nov 2026 | A01 | Business Analyst, Data Analyst | 0 Critical |
| M1 | Milestone: Project Mobilized | 0 | 09 Nov 2026 | 09 Nov 2026 | A02, A03 | Project Manager | 0 Critical |
| P2 | PHASE 2: DATA PREPARATION & REQUIREMENTS |  |  |  |  |  |  |
| A04 | Data profiling and quality assessment | 5 | 10 Nov 2026 | 16 Nov 2026 | M1 | Data Scientist, Data Analyst | 0 Critical |
| A05 | Data cleaning and standardization | 8 | 17 Nov 2026 | 26 Nov 2026 | A04 | Data Scientist, Data Analyst | 0 Critical |
| A06 | Data validation and reconciliation checks | 4 | 27 Nov 2026 | 02 Dec 2026 | A05 | Data Scientist, QA Tester | 0 Critical |
| A07 | Requirements workshops with ShopSmart managers | 6 | 10 Nov 2026 | 17 Nov 2026 | M1 | Business Analyst, Project Manager | 11 |
| M2 | Milestone: Clean Dataset and Requirements Baseline | 0 | 02 Dec 2026 | 02 Dec 2026 | A06, A07 | Project Manager | 0 Critical |
| P3 | PHASE 3: DATA ANALYTICS & DATA SCIENCE |  |  |  |  |  |  |
| A08 | Exploratory data analysis and statistical insights | 7 | 03 Dec 2026 | 11 Dec 2026 | M2 | Data Scientist | 0 Critical |
| A09 | Sales dashboard development | 8 | 03 Dec 2026 | 14 Dec 2026 | M2 | Data Analyst | 18 |
| A10 | Customer dashboard development | 7 | 03 Dec 2026 | 11 Dec 2026 | M2 | Data Analyst | 19 |
| A11 | Store performance dashboard development | 6 | 15 Dec 2026 | 22 Dec 2026 | A09 | Data Analyst | 18 |
| A12 | Inventory dashboard development | 6 | 14 Dec 2026 | 21 Dec 2026 | A10 | Data Analyst | 19 |
| A13 | Executive analytics report | 4 | 23 Dec 2026 | 30 Dec 2026 | A11, A12 | Business Analyst, Data Analyst | 18 |
| A14 | Feature engineering pipeline | 8 | 14 Dec 2026 | 23 Dec 2026 | A08 | Data Scientist | 0 Critical |
| M3 | Milestone: Analytics and Feature Pipeline Complete | 0 | 30 Dec 2026 | 30 Dec 2026 | A13, A14 | Project Manager | 18 |
| P4 | PHASE 4: MACHINE LEARNING |  |  |  |  |  |  |
| A15 | Sales forecasting model development | 12 | 24 Dec 2026 | 13 Jan 2027 | A14 | Machine Learning Engineer | 4 |
| A16 | Customer segmentation model | 8 | 24 Dec 2026 | 07 Jan 2027 | A14 | Data Scientist | 0 Critical |
| A17 | Product recommendation prototype | 8 | 08 Jan 2027 | 19 Jan 2027 | A16 | Data Scientist, Machine Learning Engineer | 0 Critical |
| A18 | Model evaluation and evaluation report | 5 | 20 Jan 2027 | 26 Jan 2027 | A15, A17 | Machine Learning Engineer, QA Tester | 0 Critical |
| P5 | PHASE 5: GENERATIVE AI |  |  |  |  |  |  |
| A19 | Prompt library design and testing | 8 | 03 Dec 2026 | 14 Dec 2026 | M2 | Generative AI Engineer | 4 |
| A20 | Retail report generator | 7 | 15 Dec 2026 | 23 Dec 2026 | A19 | Generative AI Engineer | 4 |
| A21 | AI Retail Copilot development (Stream lit) | 12 | 24 Dec 2026 | 13 Jan 2027 | A20 | Generative AI Engineer | 4 |
| A22 | Copilot integration with data and forecasting model | 5 | 14 Jan 2027 | 20 Jan 2027 | A21, A15 | Generative AI Engineer, Machine Learning Engineer | 4 |
| P6 | PHASE 6: TESTING & QUALITY ASSURANCE |  |  |  |  |  |  |
| M4 | Milestone: All Work stream Deliverables Built | 0 | 26 Jan 2027 | 26 Jan 2027 | A18, A22, M3 | Project Manager | 0 Critical |
| A23 | Dashboard quality review and data accuracy testing | 4 | 27 Jan 2027 | 01 Feb 2027 | M4 | QA Tester, Data Analyst | 2 |
| A24 | Code review and model testing | 5 | 27 Jan 2027 | 02 Feb 2027 | M4 | QA Tester, Machine Learning Engineer | 1 |
| A25 | Copilot testing and prompt evaluation | 6 | 27 Jan 2027 | 03 Feb 2027 | M4 | QA Tester, Generative AI Engineer | 0 Critical |
| A26 | User acceptance testing with ShopSmart managers | 5 | 04 Feb 2027 | 10 Feb 2027 | A23, A24, A25 | Business Analyst, QA Tester | 0 Critical |
| A27 | Defect fixing and retesting | 5 | 11 Feb 2027 | 17 Feb 2027 | A26 | Data Analyst, Machine Learning Engineer, Generative AI Engineer | 0 Critical |
| M5 | Milestone: Deliverables Accepted | 0 | 17 Feb 2027 | 17 Feb 2027 | A27 | Project Manager | 0 Critical |
| P7 | PHASE 7: DOCUMENTATION, PRESENTATION & CLOSURE |  |  |  |  |  |  |
| A28 | Project and technical documentation | 7 | 27 Jan 2027 | 04 Feb 2027 | M4 | Project Manager, Business Analyst | 9 |
| A29 | User training and handover sessions | 3 | 18 Feb 2027 | 22 Feb 2027 | M5 | Business Analyst, Data Analyst | 1 |
| A30 | Final business presentation preparation | 4 | 18 Feb 2027 | 23 Feb 2027 | M5, A28 | Project Manager, Data Analyst | 0 Critical |
| A31 | Final presentation to ShopSmart leadership | 1 | 24 Feb 2027 | 24 Feb 2027 | A29, A30 | Project Manager | 0 Critical |
| A32 | Project closure, lessons learned and repository finalization | 3 | 25 Feb 2027 | 01 Mar 2027 | A31 | Project Manager | 0 Critical |
| M6 | Milestone: Project Closed | 0 | 01 Mar 2027 | 01 Mar 2027 | A32 | Project Manager | 0 Critical |

## Milestone schedule

| ID | Milestone | Date | Working day | What it proves |
| --- | --- | --- | --- | --- |
| M1 | Project Mobilized | 09 Nov 2026 | 6 | Team set up, tools and datasets ready, governance running |
| M2 | Clean Dataset and Requirements Baseline | 02 Dec 2026 | 23 | Data cleaned and reconciled, requirements baseline with ShopSmart |
| M3 | Analytics and Feature Pipeline Complete | 30 Dec 2026 | 41 | Dashboards, executive report and feature pipeline complete |
| M4 | All Work stream Deliverables Built | 26 Jan 2027 | 59 | Models, dashboards and AI Retail Copilot built and integrated |
| M5 | Deliverables Accepted | 17 Feb 2027 | 75 | Testing passed, UAT signed, defects closed, ShopSmart accepts deliverables |
| M6 | Project Closed | 01 Mar 2027 | 83 | Presentation delivered, handover done, closure report approved |

Non-working days used: 25 Dec 2026 (Christmas Day), 28 Dec 2026 (Boxing Day (observed)), 01 Jan 2027 (New Year's Day). Moveable religious holidays are not pre-loaded.

# 4. Gantt Chart

Red bars are critical path activities, blue bars have floats (light blue shows the available slack), gold diamonds are milestones, and arrows show Finish to Start dependencies. A full resolution copy is supplied as Gantt_Chart.png, and a weekly Gantt view is in the Excel workbook.

# 5. Critical Path Analysis

| Measure | Result |
| --- | --- |
| Total project duration | 83 working days (02 Nov 2026 to 01 Mar 2027) |
| Critical activities | 16 of 32 activities (plus all 7 milestones) |
| Activities with float | 16 non milestone activities, with float from 1 to 18 days |
| Method | Critical Path Method: forward pass for early dates, backward pass for late dates, float = late start minus early start |

## 5.1 Critical path

A01  >  A03  >  M1  >  A04  >  A05  >  A06  >  M2  >  A08  >  A14  >  A16  >  A17  >  A18  >  M4  >  A25  >  A26  >  A27  >  M5  >  A30  >  A31  >  A32  >  M6

| ID | Critical activity | Dur. | Start | Finish |
| --- | --- | --- | --- | --- |
| A01 | Project kick-off and sign-off of execution plan | 2 | 02 Nov 2026 | 03 Nov 2026 |
| A03 | Dataset handover and file validation (9 CSV files and data dictionary) | 4 | 04 Nov 2026 | 09 Nov 2026 |
| M1 | Milestone: Project Mobilized | 0 | 09 Nov 2026 | 09 Nov 2026 |
| A04 | Data profiling and quality assessment | 5 | 10 Nov 2026 | 16 Nov 2026 |
| A05 | Data cleaning and standardization | 8 | 17 Nov 2026 | 26 Nov 2026 |
| A06 | Data validation and reconciliation checks | 4 | 27 Nov 2026 | 02 Dec 2026 |
| M2 | Milestone: Clean Dataset and Requirements Baseline | 0 | 02 Dec 2026 | 02 Dec 2026 |
| A08 | Exploratory data analysis and statistical insights | 7 | 03 Dec 2026 | 11 Dec 2026 |
| A14 | Feature engineering pipeline | 8 | 14 Dec 2026 | 23 Dec 2026 |
| A16 | Customer segmentation model | 8 | 24 Dec 2026 | 07 Jan 2027 |
| A17 | Product recommendation prototype | 8 | 08 Jan 2027 | 19 Jan 2027 |
| A18 | Model evaluation and evaluation report | 5 | 20 Jan 2027 | 26 Jan 2027 |
| M4 | Milestone: All Work stream Deliverables Built | 0 | 26 Jan 2027 | 26 Jan 2027 |
| A25 | Copilot testing and prompt evaluation | 6 | 27 Jan 2027 | 03 Feb 2027 |
| A26 | User acceptance testing with ShopSmart managers | 5 | 04 Feb 2027 | 10 Feb 2027 |
| A27 | Defect fixing and retesting | 5 | 11 Feb 2027 | 17 Feb 2027 |
| M5 | Milestone: Deliverables Accepted | 0 | 17 Feb 2027 | 17 Feb 2027 |
| A30 | Final business presentation preparation | 4 | 18 Feb 2027 | 23 Feb 2027 |
| A31 | Final presentation to ShopSmart leadership | 1 | 24 Feb 2027 | 24 Feb 2027 |
| A32 | Project closure, lessons learned and repository finalization | 3 | 25 Feb 2027 | 01 Mar 2027 |
| M6 | Milestone: Project Closed | 0 | 01 Mar 2027 | 01 Mar 2027 |

## 5.2 Activities with slack (float)

These activities can slip by up to their float without moving the finish date. Float is shared along a path, so using it on one activity reduces it on the next.

| ID | Activity | Dur. | Start | Finish | Float (days) |
| --- | --- | --- | --- | --- | --- |
| A02 | Tools, access and environment setup (Power BI, Python, GitHub, API keys) | 3 | 04 Nov 2026 | 06 Nov 2026 | 1 |
| A07 | Requirements workshops with ShopSmart managers | 6 | 10 Nov 2026 | 17 Nov 2026 | 11 |
| A09 | Sales dashboard development | 8 | 03 Dec 2026 | 14 Dec 2026 | 18 |
| A10 | Customer dashboard development | 7 | 03 Dec 2026 | 11 Dec 2026 | 19 |
| A11 | Store performance dashboard development | 6 | 15 Dec 2026 | 22 Dec 2026 | 18 |
| A12 | Inventory dashboard development | 6 | 14 Dec 2026 | 21 Dec 2026 | 19 |
| A13 | Executive analytics report | 4 | 23 Dec 2026 | 30 Dec 2026 | 18 |
| A15 | Sales forecasting model development | 12 | 24 Dec 2026 | 13 Jan 2027 | 4 |
| A19 | Prompt library design and testing | 8 | 03 Dec 2026 | 14 Dec 2026 | 4 |
| A20 | Retail report generator | 7 | 15 Dec 2026 | 23 Dec 2026 | 4 |
| A21 | AI Retail Copilot development (Stream lit) | 12 | 24 Dec 2026 | 13 Jan 2027 | 4 |
| A22 | Copilot integration with data and forecasting model | 5 | 14 Jan 2027 | 20 Jan 2027 | 4 |
| A23 | Dashboard quality review and data accuracy testing | 4 | 27 Jan 2027 | 01 Feb 2027 | 2 |
| A24 | Code review and model testing | 5 | 27 Jan 2027 | 02 Feb 2027 | 1 |
| A28 | Project and technical documentation | 7 | 27 Jan 2027 | 04 Feb 2027 | 9 |
| A29 | User training and handover sessions | 3 | 18 Feb 2027 | 22 Feb 2027 | 1 |

## 5.3 Potential schedule risks

- Data quality (A04, A05, A06). All three sit on the critical path. Duplicate, missing or badly formatted records would delay cleaning and push back every work stream that follows.

- Modeling chain (A14, A16, A17, A18). These tasks run one after another on the critical path, so an estimation error in any of them moves the finish date. A15 and A21 are the longest tasks at 12 days each.

- Holiday period. A15, A16 and A21 start on 24 December 2026 and run across 25 December, 28 December and 1 January, so leave and reduced availability could cost working days.

- UAT availability (A26). UAT is critical and relies on ShopSmart managers being released from daily work.

- Near critical tasks. The whole Generative AI chain (A19 to A22) and A15 have only 4 days of float, A24 and A29 have 1 day and A23 has 2 days, so they behave almost like critical tasks.

- API limits (A19 to A25). Rate limits or cost caps on the OpenAI or Gemini service could stall the copilot chain, which has only 4 days of float.

## 5.4 How delays on critical activities affect completion

Critical activities have zero float, so every working day of delay moves go live and project closure by one working day unless the team recovers time elsewhere. Non critical activities absorb delay up to their float. The scenarios below were calculated with the same schedule model:

| Delay scenario | New finish date | Delay to project |
| --- | --- | --- |
| A05 Data cleaning runs 4 days over | 05 Mar 2027 | 4 working days |
| A17 Recommendation prototype runs 5 days over | 08 Mar 2027 | 5 working days |
| A25 Copilot testing runs 3 days over | 04 Mar 2027 | 3 working days |
| A15 Forecasting model runs 3 days over (within 4 days of float) | 01 Mar 2027 | None (absorbed by float) |
| A15 Forecasting model runs 7 days over (float exceeded) | 04 Mar 2027 | 3 working days |
| A09 Sales dashboard runs 10 days over (within 18 days of float) | 01 Mar 2027 | None (absorbed by float) |

Recovery options when a critical task slips: add resource to the task (for example a second Data Analyst on A05 data cleaning), run tasks in parallel where logic allows (for example start the copilot test cases while dashboards are still being tested), reduce scope within the task through the change process, and use contingency reserve for overtime or external help. Because a 5 day slip on A17 would move the finish from 01 Mar 2027 to 08 Mar 2027, the Project Manager reviews critical task progress every week.

# 6. Resource Allocation Plan

## 6.1 Human resources

Utilization is budgeted days per person divided by the 83 day project duration. Critical path activities are staffed first, and the Project Manager checks weekly that no person is double booked on overlapping critical work.

| Role | Qty | Days each | Utilization | Key responsibilities |
| --- | --- | --- | --- | --- |
| Project Manager | 1 | 83 | 100% | Plan, schedule, budget, risks, reporting, stakeholder management, change control |
| Business Analyst | 1 | 40 | 48% | Requirements, stakeholder workshops, UAT coordination, user training |
| Data Analyst | 2 | 45 | 54% | Dashboards, data cleaning support, executive reporting |
| Data Scientist | 1 | 50 | 60% | Data profiling and cleaning, exploratory analysis, feature engineering, segmentation |
| Machine Learning Engineer | 1 | 40 | 48% | Forecasting model, recommendation prototype, model evaluation, integration |
| Generative AI Engineer | 1 | 45 | 54% | Prompt library, report generator, Stream lit Retail Copilot |
| QA Tester | 1 | 25 | 30% | Data validation, code review, testing, UAT support |

## 6.2 Software resources

| Tool | Purpose | Users | Used in |
| --- | --- | --- | --- |
| Power BI Pro | Dashboards and sharing with managers | 12 users | A09 to A13, A23, A26 |
| Python and Jupiter Notebook (open source) | Cleaning, analysis, feature engineering, modeling | Data team | A04 to A22 |
| VS Code (free) | Code development and review | Data team | A14 to A27 |
| GitHub | Version control and project repository | 8 users | A02 to A32 |
| Stream lit (open source) | Interface for the AI Retail Copilot | GenAI engineer | A21, A22 |
| OpenAI or Gemini API | Language model for the copilot and report generator | GenAI engineer | A19 to A25 |
| Jira or ClickUp | Task tracking and status reporting | 8 users | All |

## 6.3 Hardware resources

| Item | Qty | Purpose | Needed for |
| --- | --- | --- | --- |
| High spec laptops | 2 | Model training and copilot development | A15 to A22 |
| External drives and peripherals | 8 | Data transfer and workstation set up | A02, A03 |
| Secure backup storage device | 1 | Backup of cleaned datasets and models | A05 to A32 |

## 6.4 External services

| Service | Purpose | Linked activity |
| --- | --- | --- |
| Data protection adviser | Review of NDPA compliance for customer data | A04, A19 |
| Independent security reviewer | Security review of the AI Retail Copilot | A25 |
| Venue and logistics provider | Workshops and final presentation | A07, A31 |

## 6.5 Team responsibilities (RACI)

R Responsible, A Accountable, C Consulted, I Informed. PM Project Manager, BA Business Analyst, SA Solution Architect, DE Data Engineer, DS Data Scientist, BI BI Developer, QA QA Lead, Sec Security Specialist, CTL Change and Training Lead.

| Deliverable | Sponsor | PM | BA | DA | DS | MLE | GAI | QA | ShopSmart |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Execution plan and governance | A | R | C | I | I | I | I | I | C |
| Data profiling, cleaning and validation | I | A | C | R | R | I | I | C | I |
| Requirements and workshops | C | A | R | C | C | C | C | I | C |
| Dashboards and executive report | I | A | C | R | C | I | I | C | C |
| Feature engineering and statistical insights | I | A | C | C | R | C | I | I | I |
| Forecasting and segmentation models | I | A | C | I | R | R | I | C | I |
| Prompt library and AI Retail Copilot | I | A | C | I | I | C | R | C | C |
| Testing and defect resolution | I | A | C | C | C | C | C | R | I |
| UAT and acceptance | A | R | R | C | I | I | I | C | C |
| Training, final presentation and closure | A | R | C | C | I | I | I | I | C |

# 7. Project Budget

All figures are indicative estimates in Nigerian Naira (₦), built from role day rates, license prices and cloud run rates. Total = quantity x unit cost x duration.

## 7.1 Budget summary

| Category | Amount (USD) | % of total |
| --- | --- | --- |
| Personnel | ₦49,100,000 | 69.1% |
| Software Licenses | ₦1,504,000 | 2.1% |
| Hardware | ₦4,330,000 | 6.1% |
| Cloud Services | ₦3,120,000 | 4.4% |
| External Services | ₦3,300,000 | 4.6% |
| Training | ₦2,100,000 | 3.0% |
| Base budget (subtotal) | ₦63,454,000 | 89.3% |
| Contingency reserve (12% of base) | ₦7,614,480 | 10.7% |
| TOTAL PROJECT BUDGET | ₦71,068,480 | 100.0% |

## 7.2 Detailed cost estimate

| Category | Item | Basis | Qty | Unit (USD) | Mult. | Total (USD) |
| --- | --- | --- | --- | --- | --- | --- |
| Personnel | Project Manager | 1 FTE for the full duration | 1 | ₦150,000 | 83 | ₦12,450,000 |
| Personnel | Business Analyst | Requirements, UAT, training | 1 | ₦120,000 | 40 | ₦4,800,000 |
| Personnel | Data Analyst | 2 people, dashboards and data support | 2 | ₦100,000 | 45 | ₦9,000,000 |
| Personnel | Data Scientist | Cleaning, EDA, features, segmentation | 1 | ₦140,000 | 50 | ₦7,000,000 |
| Personnel | Machine Learning Engineer | Forecasting and recommendation models | 1 | ₦160,000 | 40 | ₦6,400,000 |
| Personnel | Generative AI Engineer | Prompt library and AI Retail Copilot | 1 | ₦160,000 | 45 | ₦7,200,000 |
| Personnel | QA Tester | Validation, code review, testing | 1 | ₦90,000 | 25 | ₦2,250,000 |
| Software Licenses | Power BI Pro licenses | 12 users, 4 months | 12 | ₦22,000 | 4 | ₦1,056,000 |
| Software Licenses | GitHub Team | 8 users, 4 months | 8 | ₦6,000 | 4 | ₦192,000 |
| Software Licenses | Project tracking tool (Jira or ClickUp) | 8 users, 4 months | 8 | ₦8,000 | 4 | ₦256,000 |
| Software Licenses | Open source tools (Python, Jupiter, VS Code, Stream lit) | No license fee | 1 | ₦0 | 1 | ₦0 |
| Hardware | High spec laptops for model training | Purchase | 2 | ₦1,800,000 | 1 | ₦3,600,000 |
| Hardware | External drives and peripherals | Purchase | 8 | ₦60,000 | 1 | ₦480,000 |
| Hardware | Secure backup storage device | Purchase | 1 | ₦250,000 | 1 | ₦250,000 |
| Cloud Services | LLM API usage (OpenAI or Gemini) for development and testing | Monthly, 4 months | 1 | ₦450,000 | 4 | ₦1,800,000 |
| Cloud Services | Cloud storage and compute for model training | Monthly, 4 months | 1 | ₦250,000 | 4 | ₦1,000,000 |
| Cloud Services | Stream lit prototype hosting | Monthly, 4 months | 1 | ₦80,000 | 4 | ₦320,000 |
| External Services | Data protection (NDPA) review | Fixed fee | 1 | ₦1,500,000 | 1 | ₦1,500,000 |
| External Services | Independent security review of the AI Retail Copilot | Fixed fee | 1 | ₦1,200,000 | 1 | ₦1,200,000 |
| External Services | Workshop and final presentation logistics | Fixed fee | 1 | ₦600,000 | 1 | ₦600,000 |
| Training | Team up skilling (Power BI and prompt engineering) | 8 team members | 8 | ₦75,000 | 1 | ₦600,000 |
| Training | ShopSmart manager training sessions | 3 sessions | 3 | ₦400,000 | 1 | ₦1,200,000 |
| Training | Training materials and user guides | Fixed | 1 | ₦300,000 | 1 | ₦300,000 |

For Personnel, Qty is head count, Unit is the day rate and Mult. is days per person. For recurring costs, Mult. is the number of months.

## 7.3 Contingency allocation

| Risk theme | Share | Amount (USD) |
| --- | --- | --- |
| Data quality and missing records | 35% | ₦2,665,068 |
| Delivery delays and schedule pressure | 25% | ₦1,903,620 |
| API limits and technical integration | 25% | ₦1,903,620 |
| Budget, price changes and scope changes | 15% | ₦1,142,172 |
| Total contingency reserve | 100% | ₦7,614,480 |

The 12% rate reflects the uncertainty in data quality, API usage and price changes. The Project Manager may release up to ₦500,000 per event; larger releases need Sponsor approval. Any unused reserve is returned at closure.

## 7.4 Budget assumptions

- Day rates and license prices are planning figures and will be confirmed with AnalystLab Finance and the vendors before kickoff.

- Existing office software, internet access and team workstations are reused and are not charged to the project. Python, Jupiter, VS Code and Stream lit are open source.

- Cloud and API services are budgeted for 4 months, covering development, testing and handover. There is no live production deployment.

- Spend is tracked monthly against this baseline and reported to the Steering Committee.